## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Out of 50 customers, 36 customers had overall good experience with tablet | In question number 3 of survey result, we can see that good has got 40% and great has got 32% rating | As satisfied customers, how can we improve their experience further
Customers | Went well | Maximum number of waiters were able to guide the customer pretty well while using the tablet | In question number 4 of sruvey result, "Very well" has got 76% rating out of all the responses | We can conduct a revision training for the waiters who were not able to instruct the customers efficiently
Customers | Went well | Maximum number of customers have told that navigating the tablet fairly easy to use. | In question number 5 of the survey result, most of the customers fall in between the category of neutral to very easy. | We can focus on customers who we not able to navigate tablet easily and consider their feedback for improvements
Customers | Needs improvement | Out of 50, maximum number of customers are not using tablet for ordering food after first time. | In the question number 2 of the survey, 64% customers have chosen "No" as the answer | We need to focus on why customers are not choosing tablet for placing orders after the first time.
Customers | Needs improvement | More than half of the total customers had to wait more that 15 minutes for the table | In the question number 7 of the survey, 54% customers have chosen "15+ min." as the answer | We need to find out where the delay is happing, from the customer's end for placing order or BOH staff navigating the tablet.
Customers | Needs improvement | Only 72% customers have said that their orders were prepared correctly | In the question number 9 of the survey, we can see the 28% customers have answered "No" as that answer and our target is 98% | We need to take feedback from BOH staff about what issues are they facing
Project team | Needs improvement | No reduction in table turn time | Alex mentioned in the restrospective meeting | We need to reduce the steps taken while placing and receiving orders by customers and BOH staff respectively.
Project team | Needs improvement | There are still quite a few cases of comping | Mentioned by Zane in retrospective | talk to both customer and BOH staff about this.
Project team | Needs improvement | Not enough participant for the birthday club | Mentioned by Seydou | Promote the tablet rollout to increase the number of customers
Project team | Went well | Smooth ticket flow | Mentioned by Zane in retrospective
Project team | Went well | Implementing positive changes to kitchen operations | Mentioned by Larissa in retrospective
Project team | Went well | Updates coming to website and tablets for implementing cleaner interface | Mentioned by Seydou | Focus on updating the interface to avoid any technical issues